## Sheet1
story | story desc | sprint | story points | dependant story
1 | creation of db tables like users, Medicines | Sprint-1 | 1
2 | Users beans class and Medicines beans | Sprint-1 | 1
3 | User repository and sign in validations | Sprint-1 | 3 | 2
4 | user service to store user, extract users, update user, delete user | Sprint-1 | 1 | 3
5 | Enhance user service to avoid duplicates while storing users and sign in validations etc | Sprint-1 | 1 | 3
6 | user controller for data for crud operations | Sprint-1 | 3 | 2 and 3
7 | Medicine repository
8 | Medicine service to store Medicine, extract Medicine, update Medicine, delete Medicine | Sprint-1 | 3 | 7
9 | Search medicine by name, duplicate check etc | Sprint-1 | 3 | 7 and 8
10 | Medcinine controller for data for crud operations | Sprint-1 | 3 | 9
11 | Creation of Post man collection for the user, medicine API | Sprint-1 | 3
12 | Creation of Angular Project - For UI development | Sprint-2 | 3
13 | Creation of component, class and service for Users | Sprint-2 | 3
14 | Enhance service to invoke REST API for CRUD operations | Sprint-2 | 5 | 6 and 10
15 | Enhance user component TS include/invoke CRUD operations | Sprint-2 | 5 | 14
16 | Develop user HTML page to do Admin roles | Sprint-2 | 1 | 15
17 | Create new components login and register | Sprint-2 | 3
18 | Enhance service to include signin validation | Sprint-2 | 3
19 | Create new component sign, register and develop signin and register pages | Sprint-3 | 3
20 | Create new component medicine, and service and develop medicine and register pages | Sprint-3 | 5